## Sheet1
Week | Amanda | Anna | Courtney
5/19-5/26 | Desgin main party sprites. (At least 2 of them) | Design and make world map (Optional make maps for dungeons to bosses) | Desgin skill trees for each class (Optional: Start working on overall plot) |  | 9 Bosses |  | 3 main branches for each class | Bosses made: 3 | Party charcaters made: 4
5/27-6/2 | Design Main part sprites (Finish main party sprites. Optional: work on boss sprites) | Decide on if we have dungeon maps or not. Make at least 5 boss spots. Work on how to implement the classes and skill trees. Design main menu | Map out overall plot of game. Start working on potential values for boss health and what gear stats characters should be at for each boss |  | Would be cool if final boss had multiple forms | Need to have basic dialouge scenes | Game has to be challenging but not punishing | Monsters made: 19 | Boss locations/dungeons made: 0
6/3-6/9 | Work on boss sprites and dialouge for the story | Start implementing gear drops from bosses as well as exp points. Do not have to have the value correct just need the function in place | Get the gear values characters should be at for each boss. Work out the gear values random battles should drop for what boss they are near, and gear values bosses should drop |  | Probably at MINIMUM 50 monsters for random battles |  |  | Story locked bosses: 0 | Class skill trees made: 4
6/10-6/16 | Work on random mob sprites and dialouge for story | Work on implementing random battles and add in gear values to dropped gear | Finalize initial gear values and work on boss values and monster values as well as boss mechanics and monster abilities
6/17-6/23 | Work on random mob sprites and dialouge for story | Start testing initial values and report feedback. Start importing sprites to game for each role(party, npc, boss, monster) | Work on random mob sprites and help finalize dialouge for the story
6/24-6/30 | Work on any sprites that need to be added to the game at this time | Import all made sprites into game as well as dialouge/story | Fix values based on feedback, work on any sprites that need to be added
7/1-7/7 | Finalize any sprites in the works and start testing the game | Continue importing sprites and story. If time, make sprites . Change any stat values that were changed | Test the game
7/8-7/14 | Test game | Test game | Test game
7/15-7/21 | Create any additional sprites that may need to be added | Work on importing any last minute addtions and changes | Change any stat values that need to be fixed
7/22-7/28 | Test game | Test game | Test game
7/29-8/4 | Create poster | Create poster | Create poster | Week Project is finished. We are presenting this week
8/5-8/11 | Poster Present | Poster Present | Poster Presentt